## Event Planning Checklist
Event Planning Checklist for In-Person Events |  | Event name: | (type name of event)
|  | Event date: | (type event date)
This Checklist has been created working with thousands of event organizers from all types and al sectors for more than 10 years. It's a document that we hope will help you better plan your events with your team and with your partners.
Check Done | Tasks | Due Date | Who is responsible | Additional Notes, Details and Remarks | Usuful Resources and Information
(Select the box below when the task is done) |  | (Type due date) | (Type name of responsible persons) | (Type additional interesting information)
1st Phase - At least 2 months before the event: Define the event's purpose, set a budget, assemble a team, and start the marketing plan
FALSE | Write your Event Master Plan
FALSE | Determine Specific Objectives |  |  | (For instance: attract 300 attendees and earn X sales on tickets)
FALSE | Set KPIs for Performance Tracking |  |  | (Attendance rate, social media mentions, number of sales, etc) | https://www.eventtia.com/en/blog/how-to-measure-your-event-kpis-and-drive-positive-roi
FALSE | Summarize Key Event Details |  |  | (Include the event name, date, location, and critical requirements)
FALSE | Identify and Describe Your Target Audience |  |  |  | https://www.eventtia.com/en/blog/how-to-identify-the-right-audience-for-your-events
FALSE | Explain What Makes the Event and Its Products or Promotions Unique
FALSE | Map Out Your Pre- and Post-Event Marketing Strategy |  |  |  | https://www.eventtia.com/en/blog/use-event-marketing-promote-products
FALSE | Build the Event Program and Schedule
FALSE | Determine How to Generate Revenue |  |  |  | https://www.eventtia.com/en/blog/how-to-monetize-your-events-and-increase-your-revenue
FALSE | Ensure Safety |  |  | (Plan for crowd control, emergency exits, and first aid provisions)
FALSE | Secure Event Venue
FALSE | Select the Location |  |  | (Consider factors like size, past foot traffic, proximity to your audience)
FALSE | Survey and Inspect |  |  | (Verify attendee capacity, arrange seating, product displays, stage, etc.)
FALSE | Obtain Permits |  |  | (Find and get required permits or permissions)
FALSE | Create a Detailed Budget |  |  |  | https://www.eventtia.com/en/blog/the-complete-guide-to-creating-a-budget-for-an-event
FALSE | Allocate Funds for Venue and Infrastructure |  |  | (Consider rental costs for your chosen location)
FALSE | Budget for Equipment |  |  | (Include expenses for lighting, sound systems, display stands, etc.)
FALSE | Ensure Adequate Insurance |  |  | (Cover liabilities)
FALSE | Guarantee Technical Support |  |  | (Budget for platform subscriptions, camera setups, and other tech)
FALSE | Plan for Guest Engagement |  |  | (Include fees for celebrities, influencers, experts, etc.) | https://www.eventtia.com/en/attendee-engagement-tools
FALSE | Provide Refreshments |  |  | (Budget for snacks, meals, branded drinks, etc.)
FALSE | Factor in Logistics |  |  | (Consider travel costs for team members)
FALSE | Security Personnel |  |  | (Include costs for additional security)
FALSE | Form Your Team
FALSE | Appoint Leadership |  |  | (Choose an event planner to oversee the entire process)
FALSE | Form Specialized Teams |  |  | (Create teams for logistics, marketing, customer service, etc.)
FALSE | Create Users and Assign roles |  |  | (Clearly define roles and responsibilities)
FALSE | Utilize Event Management Software |  |  | (Consider Eventtia to streamline communication and workflows) | https://www.eventtia.com/en/blog/best-event-management-platforms
FALSE | Select and Confirm Your Event Sponsors, Partners and Speakers
FALSE | Identify Relevant Sponsors and Speakers |  |  | (Choose speakers who align with your event and audience)
FALSE | Initiate Conversations |  |  | (Discuss availability, terms, and interest)
FALSE | Negotiate Fairly |  |  | (Agree on speaking fees, event exposure and partnerships)
FALSE | Ensure All Terms Are Clearly Outlined in a Contract
FALSE | Gather Materials |  |  | (Collect bios, photos, and other details for promotional use)
FALSE | Secure Events Vendors and Media
FALSE | Identify Relevant Venors and Media |  |  | (Choose speakers who align with your event and audience)
FALSE | Initiate Conversations |  |  | (Discuss availability, terms, and interest)
FALSE | Negotiate Fairly |  |  | (Agree on speaking fees, event exposure and partnerships)
FALSE | Ensure All Terms Are Clearly Outlined in a Contract
FALSE | Gather Materials |  |  | (Collect bios, photos, and other details for promotional use)
FALSE | Collaborate on Event Elements |  |  | (Ask partners to contribute to event content and promotional activities)
FALSE | Define Roles and Responsibilities |  |  | (Clearly outline each partner’s contributions)
FALSE | Establish Shared Objectives |  |  | (Agree on common goals to ensure mutual benefits)
FALSE | Maintain Communication |  |  | (Keep partners updated on event progress)
FALSE | Encourage Feedback |  |  | (Ask partners to share ideas, suggestions and concerns)
FALSE | Select the Best All-in-One Event Management Platform |  |  |  | https://www.eventtia.com/en/blog/best-event-management-platforms
FALSE | Consider Your Event Format (In-person, Virtual, Hybrid) |  |  | (In-person events need on-site check-in and activity management) | https://www.eventtia.com/en/event-management-platform
FALSE | Evaluate Features and Customer Reviews |  |  | (Look for positive reviews on Capterra.com or G2.com) | https://www.eventtia.com/en/testimonials-case-studies
FALSE | Assess User Experience and Customization Capabilities |  |  | (Opt for interfaces that are both powerful, intuitive and customizable) | https://www.eventtia.com/en/event-management-software-enterprises
FALSE | Data Insights and CRM Integrations |  |  | (Look for analytics, reports and CRM integrations) | https://www.eventtia.com/en/event-data-analytics
FALSE | Customer Support |  |  | (Choose a platform with agile and quick to reply customer support) | https://help.eventtia.com/knowledge/service-level-agreement
FALSE | Cost Considerations |  |  | (Compare pricing models to find one that fits your budget)
FALSE | Develop Your Event Branding |  |  |  | https://www.eventtia.com/en/blog/how-to-tell-the-story-of-your-brand-at-your-event
FALSE | Choose a Memorable Name |  |  | (Select a name that reflects your event's essence and brand)
FALSE | Design Visual Identity |  |  | (Create a logo that complements your branding)
FALSE | Craft a Catchy Tagline |  |  | (Develop a short, memorable phrase that captures the event's spirit)
FALSE | Imagine Branded Goodies |  |  | (Branded bags, pins, water bottles, USB keys, etc.)
FALSE | Create Your Event Marketing Plan |  |  |  | https://www.eventtia.com/en/blog/use-event-marketing-promote-products
FALSE | Develop a Strategic Blueprint |  |  | (Decide on your marketing channels, content types and partnerships)
FALSE | Create your Marketing Plan |  |  | (List and schedule your marketing plan in detail)
FALSE | Build Your Online Presence |  |  | (Create a website or webpage, social media profiles, hashtags, etc.) | https://www.eventtia.com/en/event-marketing-platform
FALSE | Set Up Event Page, RSVP, Registration Form and Online Payments |  |  |  | https://www.eventtia.com/en/blog/how-to-choose-the-best-online-registration-software-the-ultimate-guide
FALSE | Segment Attendees |  |  | (Consider Eventtia's event registration software) | https://www.eventtia.com/en/event-registration-software
FALSE | Create and Personalize RSVP or Registration Forms |  |  | (Consider Eventtia's event registration software) | https://www.eventtia.com/en/event-registration-software
FALSE | Configure and Design Badges for Attendees |  |  | (Consider Eventtia's event registration software) | https://www.eventtia.com/en/event-registration-software
FALSE | Set Up Transactional Emails |  |  | (Consider Eventtia's event registration software) | https://www.eventtia.com/en/event-registration-software
FALSE | Configure Online Payment |  |  | (Consider Eventtia's event registration software) | https://www.eventtia.com/en/event-ticketing-software
FALSE | Setup Merchandise & Goodies Order
FALSE | Create the Event Webpage |  |  | (Consider Eventtia's event registration software) | https://www.eventtia.com/en/demos
FALSE | Test Event Page, Registration Form and Online Payments |  |  | (Consider Eventtia's event registration software) | https://www.eventtia.com/en/demos
FALSE | Publish the Event Page and Registration Form |  |  | (Consider Eventtia's event registration software) | https://www.eventtia.com/en/demos
2nd Phase: 1 to 2 months before the event: Promote your event, monitor registrations and payments, prepare the logistics management activity
FALSE | Create and Share a Press Release
FALSE | Write a Concise and Engaging Story |  |  | (Around 300 words with all details without unnecessary information)
FALSE | Target Relevant Media |  |  | (Identify newspapers, magazines, TV, industry-specific publications, etc)
FALSE | Distribute to Media Entities
FALSE | Promote your Event / Execute Your Marketing Plan |  |  |  | https://www.eventtia.com/en/event-marketing-platform
FALSE | Design Appealing Event Materials |  |  | (Craft stylish invitations, posters, and tickets)
FALSE | Create and Publish Compelling Marketing Content |  |  | (Develop engaging blog posts, eye-catching ads, and storytelling videos)
FALSE | Utilize Media and Partnerships |  |  | (Prepare a detailed media kit with speaker bios and showcase sponsor logos)
FALSE | Expand Your Reach and Branding |  |  | (Promote your event on event platforms, calendars, online communities, etc.)
FALSE | Share Informative Updates |  |  | (Consider Eventtia's event marketing solution) | https://www.eventtia.com/en/demos
FALSE | Monitor Registrations & Payments
FALSE | Monitor Registrations and Payments Through Real-time Data |  |  | (Consider Eventtia's event marketing solution) | https://www.eventtia.com/en/event-marketing-platform
FALSE | Send Payment Reminders |  |  | (Consider Eventtia's event payment solutions) | https://www.eventtia.com/en/event-ticketing-software
FALSE | Venue, Catering, and Logistics Focus
FALSE | Venue Preparation |  |  | (Make necessary adjustments to your chosen location)
FALSE | Venue Accessibility |  |  | (Ensure wheelchair accessibility and amenities for differently-abled attendees)
FALSE | Venue Parking |  |  | (Arrange adequate parking or nearby alternatives if needed)
FALSE | Event Signage |  |  | (Strategically place branded signage for easy navigation)
FALSE | Security Measures |  |  | (Assess security needs and arrange for personnel or CCTV setup)
FALSE | Permits and Licenses |  |  | (Verify and obtain any required permits, insurances, or licenses)
FALSE | Catering |  |  | (Partner with a caterer to create a menu that suits the event theme)
FALSE | Audio/Visual Setup |  |  | (Prepare a checklist for necessary equipment and ensure compatibility)
FALSE | Identify and secure photrgrapher and videographer
FALSE | Configure the Event App for Attendees |  |  | (Consider Eventtia's event mobile app) | https://www.eventtia.com/en/event-mobile-app
FALSE | Set Up the On-Site Check-In App for Attendee and Partner Access |  |  | (Consider Eventtia's On site mobile app available on the App store and Play store) | https://www.eventtia.com/en/event-check-in-app
3rd Phase: 1 week to 1 month before the event: Boost marketing efforts, coordinate with speakers, solidify partnerships, and adjust ticket pricing in preparation for the event
FALSE | Ramp Up Your Event's Marketing Momentum
FALSE | Newsletters |  |  | (Send targeted newsletters to past attendees who may be interested in attending again)
FALSE | Offer Special Deals or Limited-time Offers |  |  | (Incentivize more registrations)
FALSE | Increase Your Ad Spend |  |  | (Increase advertising spending to reach a larger audience)
FALSE | Announce keynote speakers, special guests, and celebrities associated with your event
FALSE | Share Detailed Posts |  |  | (About event highlights, schedules, and what attendees can expect to build anticipation)
FALSE | Publish News Releases |  |  | (Publish your press releases prominently on your website)
FALSE | Finalize All Printed Materials |  |  | (Such as brochures, banners, and tickets, ensuring they are error-free)
FALSE | Send Informational Content to Engage Attendees |  |  | (Consider Eventtia's event marketing solutions) | https://www.eventtia.com/en/event-marketing-platform
FALSE | Coordinate Effectively with Your Speakers
FALSE | Publish Your Event Agenda / List of Speakers |  |  | (Consider Eventtia's event management platform) | https://www.eventtia.com/en/event-management-platform
FALSE | Arrange Logistics |  |  | (Consider Eventtia to organize travel, accommodation and meals) | https://www.eventtia.com/en/event-management-platform
FALSE | Collaborate on Content |  |  | (Create joint promotional materials and teasers)
FALSE | Double-check Hotel Accommodations
FALSE | Request Copies of Their Presentations |  |  | (Get speeches or scripts to align with the event's theme and prevent any overlaps)
FALSE | Arrange Technical Requirements or Props |  |  | (Find out special needs)
FALSE | Promote Event |  |  | (Encourage them to promote the event on their social media, websites, etc.)
FALSE | Strengthen Relationships with Partners and Influencers
FALSE | Confirm Commitments |  |  | (Touch base with all partners and influencers to clarify their roles)
FALSE | Document All Partnerships |  |  | (Formalize partnership agreements to protect both parties)
FALSE | Gather Event Materials |  |  | (Collect logos, promotional materials, and brand assets from partners and influencers)
FALSE | Transition from Early-Bird to Standard Pricing
FALSE | Conclude the Early-bird Offer |  |  | (Communicate the deadline to create urgency and maximize registrations before it ends)
FALSE | Introduce a New Pricing Strategy. |  |  | (Launch standard pricing or planned discounts without delay to keep ticket sales active)
FALSE | Utilize All Communication Channels |  |  | (Announce the pricing transition by emails, social media, website banners, etc)
4th Phase: 3 days to 1 week before the event: Confirm all details align with the plan, prepare backup plans, and conduct rehearsals for flawless execution
FALSE | Finalize According to the Event Master Plan
FALSE | Gather Your Team to Review the Event Plan |  |  | (Meeting to ensure everyone understands their roles)
FALSE | Confirm Venue Details |  |  | (Address, contact info, capacity, etc)
FALSE | Organize Speaker and Entertainment Logistics |  |  | (Travel, accommodation, food, etc)
FALSE | Arrange Food and Beverages
FALSE | Prepare Marketing Materials
FALSE | Schedule Event Setup and Breakdown
FALSE | Adjust the Plan Based on Team Feedback
FALSE | Prepare Backup Plans for Different Situations
FALSE | Identify Potential Risks
FALSE | Create Backup Plans for Bad Weather
FALSE | Create Backup Plans for Technical Difficulties
FALSE | Create Backup Plans for Speaker Cancellations
FALSE | Communicate Backup Plans to All Team
FALSE | Finalize the Event Script
FALSE | Develop the Event Script |  |  | (Set Introductions and conclusions for each speaker and performer)
FALSE | Create Transitions Between Segments
FALSE | Decide the Timing For Each Segment
FALSE | Share Script With Speakers and Performers |  |  | (Clarify their roles and what’s expected)
FALSE | Schedule Practice Sessions for Speakers
FALSE | Schedule Practice Sessions |  |  | (Rehearse their presentations and ensure a smooth event day)
FALSE | Give Feedback |  |  | (Help them improve their presentations)
FALSE | Organize Interviews
FALSE | Interview Speakers, Talents, and VIPs |  |  | (Promote the event and get media coverage)
FALSE | Work With the Media to Schedule Interviews |  |  | (Handle logistics like transportation and equipment)
FALSE | Organize Photo Opportunities
FALSE | Identify Photo-op Opportunities |  |  | (Plan photo opportunities for speakers, talents, VIPs, and attendees)
FALSE | Set Photo-op Locations |  |  | (Choose good locations and set up backgrounds and lighting as necessary)
FALSE | Arrange For a Photographer
FALSE | Confirm Media Guests
FALSE | Confirm Attendance and Provide Event Details |  |  | (Give them all event details like date, time, location, and schedule)
FALSE | Set Up Interviews and Provide pPasses
FALSE | Confirm Transportation, Lodging, Venue Access, etc.
FALSE | Assign Responsibilities
FALSE | Assign Tasks to Each Staff Member and Volunteer
FALSE | Ensure Clarity on Their Duties and Timelines
FALSE | Staff and Volunteer Briefing
FALSE | Brief All on Their Roles and Responsibilities
FALSE | Distribute the Event Schedule and Seating Plan
FALSE | Review Backup Plans With Them
FALSE | Inform Everyone of Their Tasks and Deadlines
FALSE | Brief Staff and Volunteers on Their Tasks and Deadlines
FALSE | Ensure Understanding of Responsibilities and Task Timelines
FALSE | Review Seating Arrangements
FALSE | Finalize Your Seating Plan |  |  | (Consider venue, event type, and attendees)
FALSE | Ensure Accessibility for Invalid Participants and Stakeholders |  |  | (Arrange clear pathways and mark wheelchair-accessible areas)
FALSE | Confirm Catering Details
FALSE | Finalize Your Food and Drink Plans With the Caterer
FALSE | Provide the Caterer With Final Attendance Numbers
FALSE | Confirm Buffet Arrangement and Catering Logistics
FALSE | Ask for Technical Help
FALSE | Contact Your Event Management Software Provider |  |  | (Consider Eventtia's event management software) | https://www.eventtia.com/en/event-management-platform
FALSE | Review All Technical Requirements |  |  | (This includes software features, integrations, and any special requests)
FALSE | Conduct Final Rehearsals and Training Sessions |  |  | (Address any issues that arise during these rehearsals)
FALSE | Confirm the Support Arrangements |  |  | (Know who your main contacts are and their responsibilities)
FALSE | Establish Clear Communication Channels |  |  | (Ensure you have direct phone lines, chat channels, or emergency emails set up)
FALSE | Manage Attendance
FALSE | Send Reminders to Attendees |  |  | (Consider Eventtia's marketing solution) | https://www.eventtia.com/en/event-marketing-platform
FALSE | Close Registration / Change to On-site Registration Mode |  |  | (Consider Eventtia's marketing solution) | https://www.eventtia.com/en/event-marketing-platform
FALSE | Prepare the Badges |  |  | (Consider Eventtia's marketing solution) | https://www.eventtia.com/en/event-marketing-platform
5th Phase: 1 to 3 days before the event: Prepare the venue with attention to decor, signage, technology, and logistics to avoid last-minute issues
FALSE | Check the Placement of All Signs for Visibility and Guidance
FALSE | Organize Registration Tables for Quick Attendee Check-in
FALSE | Test All Software to Prevent Any Technical Issues During the Event
FALSE | Thoroughly Inspect and Test A/V Equipments to Ensure Everything Works Well
FALSE | Confirm that All Marketing Materials Are Ready
FALSE | Send Reminders and Updates to Attendees |  |  | (Consider Eventtia's event management software) | https://www.eventtia.com/en/event-management-platform
6th Phase: The day of the event: Distribute materials, coordinate smoothly, and engage with stakeholders to ensure the event runs seamlessly
FALSE | Coordinate With Your Team
FALSE | Confirm Alignment Across Departments or Committees
FALSE | Remind Everyone About Job Sharing and Security Measures
FALSE | Manage Attendance
FALSE | Ensure Smooth Event Check-in With Badges or QR Codes |  |  | (Consider Eventtia's event management software) | https://www.eventtia.com/en/event-check-in-app
FALSE | Print Badges
FALSE | Manage Attendee Engagement Activities Like Live Polls, Q&A Sessions, and Quizzes |  |  | (Consider Eventtia's event management software) | https://help.eventtia.com/knowledge/how-to-print-badges
FALSE | Send Updates and Alerts by Email, SMS or Whatsapp |  |  | (Consider Eventtia's event management software) | https://www.eventtia.com/en/event-marketing-platform
FALSE | Incentivize guests and participants to actively participe, share posts on social media
FALSE | Distribute Essential Materials and Giveaways
FALSE | Provide Venue Map and Directions
FALSE | Share Emergency Contact Numbers
FALSE | Outline Key Locations
FALSE | Hand-out Seating Charts, Guest Lists, Parking passe
FALSE | Hand-out Giveways and Gifts
FALSE | Engage Stakeholders
FALSE | Check in With Partners and Influencers |  |  | (Confirm their setup and branding)
FALSE | Coordinate With Speakers or Performers |  |  | (Confirm their schedules and last minute needs)
FALSE | Offer Support |  |  | (To sponsors, speakers, and other key attendees as needed for a smooth event flow)
7th Phase: After the event: Conduct venue checks, gather feedback, thank participants, and reflect on marketing efforts to pave the way for future events
FALSE | Venue Cleanup and Inspection
FALSE | Inspect Your Venue for Items and Equipment
FALSE | Set Up a Centralized Point for Lost Items
FALSE | Catalog and Safely Store All Found Items
FALSE | Event Revenue and Budget |  |  |  | https://www.eventtia.com/en/event-data-analytics
FALSE | Collect and File All Receipts
FALSE | Calculate the Final Attendee Count |  |  | (Consider Eventtia to count and compare with registrations and RSVPs)
FALSE | Calculate and Analyze Event Revenue |  |  | (Consider Eventtia to understand customer preferences) | https://www.eventtia.com/en/event-data-analytics
FALSE | Calculate the Final Event Budget Results |  |  | (Compare actual expenditures and revenues)
FALSE | Feedback and Analysis |  |  |  | https://www.eventtia.com/en/attendee-engagement-tools
FALSE | Conduct Post-event Surveys to Gather Attendee Feedback and Insights |  |  | (Consider Eventtia's event management software) | https://help.eventtia.com/knowledge/how-to-create-a-survey
FALSE | Use Survey Data to Understand Sponsor and Performer Impact |  |  | (Consider Eventtia's event management software)
FALSE | Acknowledgments |  |  |  | https://www.eventtia.com/en/event-marketing-platform
FALSE | Send Thank-you Notes to Partners, Influencers, and Media Representatives |  |  | (Consider Eventtia's event management software)
FALSE | Email Appreciation to Speakers, Hosts, and Performers |  |  | (Consider Eventtia's event management software)
FALSE | Email Attendees to Thank Them for Participating and Share Information About Upcoming Events |  |  | (Consider Eventtia's event management software)
FALSE | Post-event Marketing |  |  |  | https://www.eventtia.com/en/event-marketing-platform
FALSE | Update or Archive the Event Website or Webpage |  |  | (Consider Eventtia's event management software)
FALSE | Distribute a Post-event Press Release Highlighting Key Moments
FALSE | Share a Highlight Reel and Event Snippets on Social Media and Via Email
FALSE | Evaluation, Insights and Lessons Learned
FALSE | Document Successes and Areas for Improvement
FALSE | Reflect on Budget Discrepancies and Lessons Learned
FALSE | Review KPIs to Assess Event Impact and ROI |  |  |  | https://www.eventtia.com/en/event-data-analytics
FALSE | Hold a Team Debrief to Discuss Successes and Areas for Improvement
FALSE | Gather Feedback From Team Members Through Surveys and Interviews
FALSE | Verify Bills With Caterers and Service Providers for Accuracy
FALSE | Organize a Short Debrief Session With Your Event Management Platform's Customer Success Team
FALSE | Leave an Honest Review of the Event Software on Capterra or G2 |  |  |  | https://www.eventtia.com/en/testimonials-case-studies
Do you have any questions or suggestions about this checklist? Feel free to share them with us by email at laurent@eventtia.com
For more practical information about event management and technology, check out Eventtia's blog.
https://eventtia.com/en/blog/the-ultimate-event-planning-checklist-7-phases-to-create-a-winning-event